## Contacts
Contact | Area of Support | Work # | Cell # | Comments
Yezdi Mistry | VP |  | 201-982-5893
Senniyappan, Jayaprakasham | G3BusinessTrack |  | 470-219-2296
Rasco, Robert | G2FirstData_MarketPlace_API |  |  | See Repository
Jason Wang | S3GDP_AccessEngMgmt |  |  | See Repository
Jess Wedlock | G3MerchantAndReporting |  |  | See Repository
SanjayKumar, Balasubramaniyan | X2WEb_GBS |  |  | See Repository
402-957-1556

## Prod Plan
Change Description
Task / Activity |  | Responsible Group | Estimated Duration Day 1
hh:mm
Pre-Implementation Tasks - list all steps that need to occur prior to the start of the change
2 | User Setup in BTS MIAM environment | G3BusinessTrack
Over-all Risk mitigation and Application/System level monitoring that will occur through out the change
1 | All stakeholders will be sent an invite with TEAMS meeting link to be utilized during the overall change window for validation and montoring. | G3BusinessTrack
Implementation Tasks - detailed step by step actions that must be performed to complete the change. - If the change is not being performed while either out of service or in a planned outage window, validation steps should be included throughout the implementation steps to ensure production is still processing. (complete step 1, validate, complete next step, validate etc.) - If taking an item out of service for implementation but not full outage, ensure validation is done prior to the start of the change that the environment is processing as expected after the item has been removed from service. - Include implementation milestones such as go/no go check points and drop dead back-out time.
A | Overall Implementation Time |  | 2 hr
1 | Cedar statement CQ5 URL need to updated to http://n1pvap234:4503/ from http://r1pvap1163:4503 Restart the instances. Test it and the request should go to n1pvap234 server. Revert the changes after DR testing. | G3BusinessTrack
Validation Tasks - detailed step by step actions that must be performed to validate the change was successful. This should include change specific validation steps as well as end to end system/application level validation to ensure there was no unintended impact from the change.
| Overall validation task: |  | 2 hr
1 | Logon to https://www.businesstrack.com Take shots from AWS logs showing traffic on both East and West regions (active - active). On the dashboard check Statements. Gather evididence from app server logs, showing that data is coming from DR server. After reverting back to Omaha, perform basic regression testing. | G3BusinessTrack
2 | Validate SSO is working for downstream Apps - PBC, CLR, TIMS & Disputes Manager (This was not changed and is just for a sanity test). | G3BusinessTrack
Montioring time
1 | Closely Monitor - Standard procedure after any change exercise | G3BusinessTrack | 12 hr
Back-out Tasks
| Overall Backout Task Time: |  | 2 hr
1 | Revert changes made for DR Test. | G3BusinessTrack
Back-out validation
| Overall Post-Backout Validation Task Time: |  | 2 hr
1 | Regression Test logon, and validate SSO is working.